## Slide 1
What methods/procedures &/or techniques are used to describe HOW the process is done.
EAGP_4-1_PE-EDS_10_EN Global Engineering Change Procedure EAEP_4-1_ME-EDS_10-01-F01_EN Feasibility Study Checklist EAEP_4-1_ME-EDS_10-01-F02_EN Engineering Change Implementation Plan EAEP_4-1_ME-EDS_10-01-F03_EN Engineering Change Coordination Letter (ECCL) ECM EAGP_4-2_PE_09_EN Engineering Permits/ Deviation Process EAEP_4-1_ME-EDS_10-01-F04_EN Template for Monitoring Engineering Change Costs EAEP_4-1_ME-EDS_10-01-F06_EN - Engineering Change Letter (ECL) EAGP_4-3_CS-EDS_05_EN Process Release for Pilots / Regular Production EAEP_4-1_ME-EDS_10-01-A01_EN PB2O Update Flow when Options-KSK Modules change EAEP_5-1_PC_08_EN Claim to OEM Process
What METRICS are used to report the effectiveness/efficiency of the process or to monitor/measure performance?
Response time to CR # Customer Complaints due to Changes not well implemented
WHAT materials, equipment, infrastructure and/or references are used in the process?
EOS Glossary Definitions
OBJECTIVE
The objective of this procedure is to provide a consistent approach for engineering changes explained in Ref. A, in terms of analysis, planning and implementation in the manufacturing plants
SCOPE
This procedure applies to all engineering changes (physical items or product documentation) , including Model Year Changes, in all EDS units / locations, subsidiaries and majority owned joint ventures in Europe
OUTPUTS Process deliverables (EOS Pipe)
Change correctly implemented ( 4.1) Change implemented on time ( 4.1)
INPUTS Triggers process to start (EOS Pipe)
Change Request ( 4.1) Customer Drawings ( 4.1) Customer Specifications ( 4.1)
WHO owns this procedure and who participates in the process? |  | 
SL Owner | ME | 
SL participants | ME, SCM, PC, MG, CS, HR, PE | 
Product Line |  | Cable
 | X | Wiring Harness
 | X | Cordset

## Slide 2
1 | ME (CIL)
Receive Change Request | 
PE (CO, CL), A, E, H | 
2 | ME (CIL)
Analyze the change | 
Project team, B | 
3 | ME (CIL) )
Is the change feasible? If “YES” go to Step 4 If “NO” go to Step 21 | 
Project team, B, E | 
4 | ME (CIL)
Consolidate the change cost and propose implementation date | 
Local Finance, Purchasing, PC , G, D, E | 
Is same product produced in more than one EDS site and is Liaison coordinator assigned?
YES
5
4a | ME (CIL)
Send information to Liaison Coordinator | 
4b | Liaison Coordinator
Align feedbacks between plants | 
ME, PE | 
Are feedbacks aligned?
5
YES
NO
NO
DETAILED PROCESS FLOW CHART

## Slide 3
10 | ME (CIL)
Prepare ME internal documents (ECL or equivalent) and define Engineering Change Implementation Planning. | 
Project team, C, H, J | 
12 | ME (CIL)
Make a periodic follow-up of the Engineering Change Implementation Plan | 
Project team, C, F, H | 
14 | Manufacturing, ME (CIL)
Implement Change / Produce 1st part | 
Project team | 
15 | Customer Satisfaction
After 1st part is checked, perform system/ process release | 
Project team | 
5 | ME (CIL) )
Send information | 
CO,CL, A, E, B, D | 
Does Customer agree?
20
6 | ME (CIL)
Receive Change Notice (CN) | 
PE (CO, CL), E | 
YES
7 | ME (CIL), PC
Analyze the change notice and Prepare Preliminary ECCL or equivalent | 
Project team, D, E | 
9 | ME (CIL)
Distribute Interim ECCL or equivalent | 
Project team, D | 
Is there a change in the cost communicated through CR after CN analysed?
8 | ME (CIL)
Submit Preliminary ECCL or equivalent with updates | 
CO, CL, Sales, D | 
Is Preliminary ECCL or equivalent approved by Sales?
20 | ME
Stop the process | 
11 | ME (CIL)
Submit ECL or equivalent for approvals. Document approved? If ‘’YES’’, Go to next step. If ‘’NO’’, Revise and submit again. | 
C,H | 
13 | PC
Ensure all coordination of the Excess & Obsolete material is completed. | 
Project Team, K | 
16 | Manufacturing
Start of Production | 
Project team | 
17 | ME ( CIL)
Distribute Final ECCL or equivalent | 
Project team, D, E | 
18 | PC
Send the 1st Shipment of changed harnesses | 
21 | ME (CIL)
Send information | 
A, B, E | 
3
4
NO
YES
NO
YES
NO
19 | PC
Proceed with Claim to OEM process | 
Sales, K | 
DETAILED PROCESS FLOW CHART

## Slide 4
Process Step # | Owner | Requirements and/or Additional Details
1 | ME (CIL) | The Change Request (CR) for all projects should be received through ECM (Ref. E). If ECM( IT application for change management) is not in use for a specific project or customer, the CR should be received by e-mail or share point.
2 | ME (CIL) | Timing for completing the feasibility analysis can be specified by customer (can be a different timing in different phases of the project) and in this case is communicated by PE to Project Team or, if customer requirements are missing, turn- around target is defined by management. If timing can not be respected, owner of the item that is in delay should inform Change Initiator/ Change Owner about the reason of delay and estimated extension needed.
3 | ME (CIL) | ME should meet with the project team from the plant to analyze if the change is feasible or not. Frequency of feasibility meetings should be adjusted in accordance with changes Lead Times ( either requested by customer, either defined by EDS Management). ME should prepare a list with new CR’s received from previous meeting, and with affected processes for those CR’s. Original CR should be analyses by every member of Project Team before the meeting. During the meeting, open points will be clarified together. If ECM is used, each responsible answer is documented in ECM. If ECM is not used, each responsible answer is documented using the Feasibility Study Checklist (Ref. B). However, if there is a single NO occurs, change will be evaluated as a not feasible change. In prototype phase consider marked specific questions.

## Slide 5
Process Step # | Owner | Requirements and/or Additional Details
4 | ME (CIL) | Consolidate Labor, Material Data, Investment & Obsoletes and Excess & Obsolete Material costs and define implementation date. In prototype production: obsolete costs are collected in phase basis. In prototype production, for the CR’s after drawing release, costs are collected. Ref G; Template for monitoring EC costs is recommended to be used or equivalent should cover all. If ECM is used, each responsible answer is documented in ECM( One Time Cost). If ECM is not used, each responsible answer is documented in ECCL( preliminary) or equivalent, depending on the Customers. (Customer templates can also be alternatively used if available and if contains all costs types that should be collected.)
4a | ME (CIL) | Each plant sends info separately to Liaison Coordinator. In case the same product is produced in more than one EDS sites, ME country managers of involved plants analyze the risk and decide if Liaison Coordinator assignment is needed.
4b | Liaison Coordinator | Liaison Coordinator makes alignment job by building the following regular meeting routines. Align the engineering level of wiring harness, cordset shipped from each location and ensure Flawless Communication ME / PE

## Slide 6
Process Step # | Owner | Requirements and/or Additional Details
5 | ME (CIL) | Change depending cost and implementation date (as mentioned on note 4), have to be sent to CO or to CL via mail by preliminary ECCL template (Ref. D), or equivalent or entered to ECM system (Ref. E), depending on the Customers. (Customer templates can also be alternatively used if available).
6 | ME (CIL) | The Change Notice (CN), can be received by e-mail, share point or through the ECM system (Ref. E).
7 | ME (CIL), PC | Based on Change Notice (CN), the Preliminary ECCL (Ref. E) or equivalent (in ECM approval is visible for all functions).must be initiated and all the steps needed for the change implementation must be identified, as well as the lead time for implementation. Also, all the costs related to the change must be confirmed (even if CR in ECM was done), such as: Excess & Obsoletes Investment & Obsoletes Rework (if needed) Overtime (if needed) Special Transportation (if needed) It is recommended to include lead time of one week between CN reception and Preliminary ECCL or equivalent submission. Exception: Some customers do not provide Change Request for analysis, directly change notice provided. In these cases, the timing agreed with customer will be obeyed.
8 | ME (CIL) | Preliminary ECCL or equivalent (in ECM approval is visible for all functions) with updates is submitted. If there is a change exist in the cost communicated through CR after CN analyzed, the Preliminary ECCL or equivalent must be submitted to CO or CL as well as to Sales Account Manager for approval. The approval should be provided via mail considering change Lead Time and customer MRD( Material required date) If there is no change between CR and CN, preliminary ECCL or equivalent will not be sent to CO or CL and Sales again.

## Slide 7
Process Step # | Owner | Requirements and/or Additional Details
9 | ME (CIL) | According to note 8 Only when ME receive the approval from CO or CL, Interim ECCL or equivalent is issued .- only if project is not in ECM ( in ECM approval is visible for all functions). The preliminary ECCL or equivalent is issued as Interim ECCL or equivalent. - only if project is not in ECM ( in ECM approval is visible for all functions). It is recommended to include lead time of 2 days between CO, CL approval and Interim ECCL or equivalent submission
10 | ME (CIL) | If CN came through ECM (Ref. E). ME informs project team about the change. ME must define which areas must be involved during the change implementation and define the team that will input in the system all the data needed. At this time, the CIL shall define a change implementation planning with all required activities, dates and responsibilities to assure the correct modification on time. All the activities considered on the Ref. C must be considered for each Engineering Change. If there are tasks not applicable, NA should be written on the status. If locally there is no Checklist in place, Ref. C should be used. ME Internal Document (ECL or equivalent) are any document(s) issued by ME (CIL) to inform project team about the details of the change; which are prepared by transferring data from original CN and for which there is possibility to make mistake while transferring data from CN.

## Slide 8
Process Step # | Owner | Requirements and/or Additional Details
11 | ME (CIL) | The ME internal document (ECL or equivalent) must be checked and approved at minimum with one step of control by ME project leader of the same or another project. Aim of the approval is to assure that internal document(s) is correct according to CN; no mistakes are done during transfer of info from CN. Approval should also have a written evidence by e-mail from the approver.
12 | ME (CIL) | During these meetings, all the tasks related to the change implementation (ECCL) or equivalent must be reviewed within the Project Team, to assure that everything will be done before the implementation date. In the case that ECM system (Ref. E) is being used, all the task owners previously assigned, must assure that their tasks are closed (sign-off done).
13 | PC | The responsibility to coordinate E&O material identification and disposition lies with PC. If E&O costs approved in CR phase are bigger than ones estimated before CN implementation, Plant Manager and PC Operation Manager should be notified. If E&O costs are between 5k and 50k Euro, PC team should notify Plant Manager and PC Operation Manager. If E&O costs are above 50k Euro, PC team should notify Regional Director and PC Director.
14 | ME (CIL) | First harness must be checked from harness drawing which is approved by customer satisfaction authority according to the original CN. All problems detected must be analyzed to eliminate their causes and correct the process, if needed.

## Slide 9
Process Step # | Owner | Requirements and/or Additional Details
17 | ME (CIL) | The final distribution of the ECCL (Ref. D) or equivalent (Actual OTC from ECM) will be made after CIL has gathered all pertinent change implementation information, but no later than two weeks after the change has been implemented in the plant, with the input of the real costs and dates per each engineering change or set of engineering changes which have the same implementation date according to the new phase/Model Year change/ Facelift. The package of Final ECCL or equivalent should have the lists if available with all changes for which ECCL is created, leads for Scrap with quantity and costs, obsolete components with quantity and costs, new equipment with costs.) For the temporary changes occurred in prototype phase and if there is a need to use alternative method / process / equipment or material, permit procedure should be followed (Ref. F)
18 | ME (CIL) | Compliance with additional identification change in the packaging, if required.
21 | ME (CIL) | If ECM is not used, ME must inform if the change is not feasible as « NO (N)» via e-mail to CO or CL. ME need to justify the reason and feasibility study checklist must be sent to CO or CL. If ECM is used, CO receives feasibility status after Feasibility check completion.

## Slide 10
RASI is mandatory
Swimlane | R - Those who do the work to complete the task | A - There must be only one accountable specified for each process output (process owner) | C - Gives consultant and support based on needs | I - Should be informed about the output, escalation, monitoring
Manufacturing Engineering​ | X |  |  | 
Environmental Health ＆ Safety-Corp.​ | X |  |  | 
Customer Satisfaction​ | X |  |  | 
Production Control​ | X |  |  | 
Product Engineering​ |  | X |  | 
Manufacturing​ | X |  |  | 
Human Resources​ | X |  |  | 
SCM Commercial (SC)​ | X |  |  | 
Sales​ | X |  |  | 
SCM Logistics (SL)​ | X |  |  | 
Finance​ | X |  |  | 
Program Management​ |  |  | X | 
Global Security​ |  |  |  | 
Information Technology​ |  |  | X | 
Legal​ |  |  |  | 
Global Trade & Compliance​ |  |  |  | 

## Slide 11
Release Date | DCR Number | Change Details | Document Owner
13.11.2008 | (DCR G070) | Re-numbered and re-formatted according to EOS standards. Content is reviewed. Old numbers were DPEW EU-MEN 03.08.01-00.001 & F1 | S. Uysal
07.10.2011 | (No DCR) | Document owner changed from S. Uysal to F. Kulan | F. Kulan
14.08.2013 | (DCR E13-10) | Scope revised to cover Model Year and procedure revised to clarify responsibilities for Excess and obsolete costs (Step 4~9 added, Step 10 reworded, Step 13 revised, Step 14-15 added, Notes 5-6-8 added and 10-11-13-14 revised, New definitions added | F. Kulan
17.05.2015 | (DCR E15-06) | Corrections of references in box 16 and note. Add interface D in boxes 6 and 8. Add question box between boxes 14 and 15. Add box 15 with note and box 24. Correction of some formulas in ECCL form. Two new items (75a and 79a) were added to the implementation checklist. | F. Kulan
21.12.2015 | (DCR E15-30) | Corrections in the flow, explain the preliminary ECCL submission in detail, add the preliminary ECCL or equivalent to define the information how to be provided. Explain the feasibility results and which information should be provided and to whom defined. New EU Prototype production process procedure relevant updates are done as prototype ECM plan, template for engineering costs. Question 132 in serial ECM plan is updated as «remove PFP» which does not available in EU systems. All feasibility study checklist is updated according to the global study that has been done. | F. Kulan
06.07.2016 | (DCR E16-10) | Correction between feasibility checklist and note 3.One formula , Process definition and change types in ECCL added, clarification of the approval process when there are changes between the first study vs preliminary ECCL or equivalent in note 11, 13, 14,15 and recommended lead time, Final ECCL as a package and content | F. Kulan
04.11.2016 | (DCR E16-27) | Revised HOW box, Steps 15 , 16 and Note 16. Added new step and note after Step 16 . Numbers of steps and notes are re-arranged, Added Not 20. | F. Kulan
08.09.2017 | (DCR E17-18) | Changed SME. Revised Steps 16, 18 and 20, Notes 5 and 20 and Definitions, added Reference I, Notes 7 and 9, removed Step 23 to close INE-PRO-01. Revised process participants and Final Approval Matrix Record. | F. Kulan

## Slide 12
Release Date | DCR Number | Change Details | Document Owner
01.01.2018 | (DCR E17-25) | Added Steps and Notes 10a and 10b and reference J to identify the flow when same product is produced in more than one Aptiv sites. Added Roles&Responsibilities section to define Liaison Coordinator role | F. Kulan
27.08.2021 | (No DCR) | Links in HOW box updated ; Logo changed from Delphi to Aptiv; step 3 linked with step 23 corrected , it was 24 ; e-Change replaced with ECM. Effective date not changed. | F. Kulan
18.04.2023 | (DCR 2417) | Removed steps from 4 to 9, update responsible in step 3, 20 , add steps 13, 18, remove ‘Excess & Obsoletes’ Metric, add one procedure in ‘How’. Numbers of steps and notes are re-arranged. Notes: 1, 2, 3, 4, 6, 7, 8, 9, 20 updated. Note 13 added. | F. Kulan
12Jan,2026 | 4403 | Combine EAEP_4-1_ME_01-F02_EN - Engineering Change Implementation Plan for Preserial & Serial with EAEP_4-1_ME_01-F05_EN - Engineering Change Implementation Plan for Prototype, under EAEP_4-1_ME_01-F02_EN - Engineering Change Implementation Plan. Remove EAEP_4-1_ME_01-F05_EN –obsolete. Adding EAEP_4-1_ME_01-F06_EN - Engineering Change Letter (ECL) Reformulate step 10 and 11 Adding ECL and ECCL in Definitions Re-numbered after step 16 due to adding step for Distribute Final ECCL or equivalent - 17 become 18; 18 become 19; 19 become 20 and 20 become 21. Document in new format, Change APTIV to EDS sites. Forms & attachment revised, Document owner changed from F. Kulan to Jurca Alina. | A. Jurca