## EAGP_4-4_MG_01-F01_EN
BUSINESS TRANSFER EXECUTION CHECKLIST
PROJECT: |  |  | INITIAL DATE:
ORIGIN PLANT: |  |  | REVISION DATE:
RECEIVING PLANT: |  |  | BUSINESS TRANSFER MANAGER :
STEP | EVENT / ACTIVITY | DEPARTMENT | OWNER | PLANNED | REAL | COMMENTS
NUMBER |  |  |  | DATE | DATE
1 | Receive Customer Notification and Conditions to execute transfer
2 | Notify Sales Dept for Customer Contract change
3 | In case of a transfer to an IGS / FSS check if the Contract is fixed and signed
4 | Define Project Timing Planning
5 | Determine Transfer Team
6 | Review Customer and Tier 1 Expectations and Requirements (ex. CSI, SQAM, GP's)
7 | Develop Capacity Study: Define Start Up Plan / Ramp up Curve / Safety Stock level needed versus Customer Demands
8 | Check level of inventory and existence of Excess & Obsolete already in manufacturing location or in the SILS / Warehouses prior to the transfer
9 | Identify potential risk of generation of Excess and Obsolete during the transfer period due to level of stock built
10 | Identify potential Engineering Changes that can occur during the transfer period
11 | Analyze the harnesses produced by the Transferring Plant versus actual Drawings and BOM's (to be done by the Receiving Plant)
12 | Get information from Customer related with schedules: are the schedules fixed and known for the complete transfer period?
13 | Product / Process Requirements:
* Calibrate all required Equipment according Aptiv and Customer Specifications - Measurement System Analysis (MSA) Specifications
* Assure Tooling release according Aptiv and Customer Specifications
* Assure Process Equipment release according Aptiv and Customer Specifications
* Assure Rework tooling release according Aptiv and Customer Specifications
* Implement Statistical Process Control (SPC) to evaluate the process
* Implement Pre-control Charts where applicable
* Research export laws and requirements from the origination point and import requirements at destination for machinery and equipment and trigger necessary actions according to HOGP_1-3_FI-TAX_01_EN Export Controls Machinery and Equipment
14 | Process Control:
* Review Process Flow Diagram (PFD)
* Analyze PFMEA between 2 Plants (with a multidisciplinary team) and review / revise PFMEA, incl. re-evaluating the risks according to the conditions in the plant receiving the transfer
* Identify KPC's / KCC's / CCS designated by Customer and/or Plant (directly in drawing and/or customer requirements)
* Re-evaluate if preventive and detection actions defined are sufficient (full proof for safety characteristic and error proof for others) to mitigate identified risks related to KPC, safety and regulatory characteristics
* Analyze Customer Complaints and respective Corrective Actions taken in the PFMEA
* Ensure that significant characteristics are included in the Control Plan
* Ensure Control Plan is included on Working Methods
* Identify and determine responsibilities for checking point inspections
* Identify checking point inspections, frequency and sample size
15 | Quality History Analysis:
* Analyze FTQ, Red Tags, Supplier's performance
* Assure that Quality Records are transferred and identify those required by Customer
* Analyze Customer Feedback (records since Project SOP )
* Ensure project lessons learned and best practices implementation at the receiving plant
16 | Contacts at Customer Plant:
* Identify Customers / Key Contacts on VAP (Vehicle Assembly Plant), Customers, SQE (Supplier Quality Engineer)
* Identify Key Contacts in the Aptiv Warehouses / SILS for the Customer
* Identify CSE (Customer Support Engineer) at VAP (if needed)
17 | New hiring personnel:
* Identify training needs (all personnel involved)
* Ensure awareness training related to key, safety and regulatory characteristics operations (all personnel involved)
* Customer specific Requirements Acceptance / Rejection criteria training for manufacturing people
* Key Stations - / Critical stations skills certification
* Generate Flexibility Charts / Operator Skills Matrix
18 | Get Customer approval for PTR (Production Trial Run) Plan (quantities and dates)
19 | Duns Code Activation:
* Implement Current Model Year Part Number
* Implement Future Model Year Part Numbers contracted by Transferring Location
20 | Verify if the purchased component Material Master SAP data is created and requirements are entered into SAP.
xxx | Verify that any changes to BOMs caused by material supplier change is handled via change request (ECM) and approved by customer (SRICA, TPD, SREA, Deviation…)
xxx | Verify that purchased component Material PPAP is approved for new suppliers or new Suppliers locations for the OEM
21 | Comply with ePPAP System - transferring of ePPAP / PPAP files (applicable when the Plant works with e-PPAP system at GSD)
22 | Shipping Control:
* Identify Customer Requirements for the Shipping Control
* Get Customer validation for Shipping Label printing
* Identify the need of SIP / FTQ usage in the Label Print (visual aids, labels related with Customer's feedback: Customer Complaints, Wiring Incident Report)
* Get Customer approval for packaging if different of Original Plant. Define flow of packaging returnable material.
23 | Sales Administration:
* Verify Direct Sales and Hub Sales, Title transfer terms and VAT credit constraints within the Country
* Check opportunities and constraints with Tax and Customs Staff / Finance
* Define SAP requirements for finish goods at the Receiving Plant: Plant codes, document types,...
24 | IT System:
* Verify IT systems and data links are changed to reflect the new plants schedule, receiving and finished goods value stream until customer receiving and invoicing
* Verify if the upgrades required for facility / utility IT systems to support the project have been completed. Equipment utility requirements will be needed to complete this work.
25 | Verify that environmental, health and safety permits have been obtained and environmental systems are in place to manage the environmental impacts of the new business activities. Process flow diagrams and materials inventories will be needed to complete this work.
26 | In case of Aftersales Production involved in the transfer:
27 | * Check if the assumptions mentioned in this checklist are also applicable and covered for the Aftersales Production
28 | Get BMG approval (if applicable)
29 | Get PPAP(s) for OEM and Tiers Approval for Receiving Plant
30 | Perform Internal Process Audit at the Receiving Plant
31 | Perform Run @ Rate Audit at the Receiving Plant
These are mandatory activities to be performed, additional ones can be added according to Manufacturing Location needs.