## Slide 1
What METRICS are used to report the effectiveness/efficiency of the process or to monitor/measure performance?
PRA Evaluation Financials according AR E&O according to forecast Order to Cash Process implemented Inexistent Premium Freight
WHO owns this procedure and who participates in the process? | 
Owner: | MG –Operational Management
Swim Lanes: | PM, ME, PE, CS, PC, MG , SE
CORP, Segment, or BU: | EDS
WHAT Materials, equipment, infrastructure, references/resources are used in the process?
Aptiv Glossary EAGP-2.6.CB1-BU-02 Business Transfer Decision EAGP-2.6.CB1-BU-02 F01 Business Transfer Concept Checklist EAGP-4.4-CS-01 Production Readiness Assessment
OBJECTIVE
The objective of this procedure is to provide a consistent process for the execution of business transfers.
SCOPE
This procedure applies to all business transfers within Aptiv SPS
OUTPUTS – Process deliverables
SOP at receiving plant Business Transfer Execution Checklist completed Close Transfer Metrics PRA report Production Readiness statement (Passed/ not Passed)
INPUTS - Triggers process to start
Management approval Customer approval Business case Timing Gaps and risk analysis Business transfer Concept Checklist ( Program Business Transfer Manager assigned
What methods/procedures &/or techniques are used to describe HOW the process is done.
Business Transfer Documentation (includes Business Case, Transfer Presentation and proposed planning, Customer Approval documents) EAGP_4-4_MG_01-F01_EN Business Transfer Execution Checklist EAGP-4.3-ME-012_EN Inter Plant Equipment Transfer Process EAGP-4.4-CS-01 Production Readiness Assessment

## Slide 2
1 | Business Transfer Manager
Receive assignment from BU Leadership | 
2 | Business Transfer Manager, Functional Management, Transferring plant, Receiving Plant
Assign members to Transfer Team | 
Business Transfer Documentation | 
3 | Business Transfer Manager, Transfer Team
Review Business Transfer Documentation and initiate activities as in Business Transfer Execution Checklist. | 
Business Transfer Documentation | 
4 | Business Transfer Manager
Present latest gaps and risks assessment, Business transfer checklist and timing plan | 
CB Director, BU Director, Operations Director | 
5 | BU Director, Operations Director, BU Director
Determine frequency and timing of subsequent reviews. Business Transfer Manager needs to include review dates in the project plan. | 
Business Transfer Manager | 
6 | Business Transfer Manager
Verify completion of Business Transfer Checklist and identify gaps and risks. Develop action plan for gap closure and risk mitigation | 
Transfer Team, Business Transfer Checklist | 
8 | Assessment Team
Review Business Transfer Execution Checklist and Action Plan closure and effectiveness | 
Transfer Team, BTM, Receiving Plant | 
Is Production Readiness Assessment needed?
Y
N
9
7 | AQP Manager
Define Project Assessment Team | 
12

## Slide 3
13 | Receiving Plant
Start production at Receiving Plant | 
Transfer Team, Operations Director | 
11 | Business Transfer Manager
Execute and validate the action plan or escalate problems in case is needed | 
Transfer Team, PBU Director, Operations Director, BU Director | 
12
12 | Business Transfer Manager
Get Harnesses BMG / PPAP and Run & Rate approval when required | 
BU Director, Customer | 
14 | Business Transfer Manager or BU
Close Transfer and Review Metrics | 
BU Director, BU Director, Operations Director | 
10 | Assessment Team
Perform the Assessment. | 
EAGP-4.4-CS-01 Production Readiness Assessment | 
9 | AQP Manager
Schedule Production Readiness Assessment. | 
Transfer Team, BTM, Receiving Plant | 
Process approved?
N
12
Y

## Slide 4
Process Step # | Owner | Requirements and/or Additional Details
1 | Business Transfer Manager | The Business Transfer Manager is the person responsible for the management and completion of the business transfer and shall be assigned within the Region according to the existing procedures.
2 | Business Transfer Manager, Functional Management, Transferring plant, Receiving Plant | Both the Receiving and Transferring Plants should have a Manufacturing Support Team which typically includes Manufacturing, PC&L, Quality Engineering and Process/Tool/Industrial Engineering, EHS. The Transfer Team consists of these two teams plus representatives from Sales, Application Engineering, Regional or Divisional Process/Tool/Industrial Engineering, Advanced PC&L or any other staff area as needed. The risk assessment done in the Business Transfer Concept checklist must be considered for all functional team members included in the transfer team definition. When ever risks are identified as high for team capabilities, an experienced transfer team from central or from mature plant must be in place to mitigate identified risk.
3 | Business Transfer Manager, Transfer Team | Business Transfer Manager initiates Business Transfer Checklist (use EAGP_4-4_MG_01-F01_EN from this procedure or an equivalent one), and he / she is responsible to define dates and responsibilities for each activity which must be in accordance with the Transfer Team.
5 | BU Director, Operations Director, BU Director | At least one meeting with Management shall be scheduled to review the Compliance level of the Business Transfer Execution Checklist.
6 | Business Transfer Manager | In case of open actions or risks identified, the Business Transfer Manager shall escalate the problems to Management during the Project Transfer Review Meeting.

## Slide 5
Process Step # | Owner | Requirements and/or Additional Details
8 | Assessment Team | The Assessment Team is responsible to approve the Manufacturing Process at the receiving plant before SOP according the Business Transfer Execution Checklist results . The Business Transfer Manager should participate in this Assessment and is under his / her responsibility the definition of the Action Plan to close the Gaps. The Assessment Team must analyze the transfer checklist and decide the Project status based on the following criteria: If Result is Yellow or Red, Production Readiness Assessment (PRA ) must be scheduled. After the EAGP-4.4-BU.01 F01 Business transfer execution check list is completed without any open action that could affect the Product, if necessary the process can run with intention of training and learning curve and no pieces will be shipped until PPAP & Run@Rate Approval.
11 | Business Transfer Manager | In case of Open Actions by the SOP timing, the Operations Director should decide if the Process can be launched. Perform Transfer Reflections if there is opportunities for improvement or Lessons Learned.
12 | Business Transfer Manager | The Transfer is completed when the Harnesses BMG( if applicable), PPAP and Run & Rate are completed for the new plant and approved by Customer . CT should be done approx. 1 month after PRA. BMG stands for Build Sample Approval and is a specific requirement from VW customer.
14 | Business Transfer Manager or BU | In some regions can be requested, that the Business Transfer Manager presents the actual Metrics and get the Management Declaration for Project Closure. From this moment onwards the Project is under the Responsibility of Plant Management.

## Slide 6
Release Date | DCR Number | Change Details | Document Owner
6/10/2008 | (DCR G414) | New document. Replaces EAGP 10.2-3. | BU
10/2/2008 | DCR G557) | Removed DCS from Scope. Revised Steps 6, 7 and 9. Revised Note 3. Deleted Note 7. | BU
11/21/2008 | (DCR G625) | Process moved from Flow 2 to Flow 4. Document number was EAGP-2.6.CB1-BU-03. Steps 35 and 36 added to Form F01 to include facilities and environmental activities. | BU
11/10/2009 01/05/2011 07/25/2011 06/07/2012 11/06/2014 5/19/2023 | DCR G754) (DCR G849) (DCR G891) (DCR G12-39) (G1131) No DCR | See all change details in Obsoleted version Sep. 2024 | BU -Gerhard Distler
10/8/2024 | DCR 2115 | Format template changed; SL owner changed from BU to MG Operations; update the DO to Antonio Andrade ; In step and Note 12 added Harnesses BMG (if applicable). In F01 changed the ownership from BU to MG, no change in content . | Antonio Andrade
12/2/2024 | 2619 | Procedure note 2 updated (risk assessment of receiving plant team capability) to reflect lessons learned from Warranty claim SQP ticket TK2024000018006/ QSYS no W-240904-001. | Antonio Andrade