## Contingency Response Team
Function | Name | E-mail | Mobile phone number | Other
Senior Management
Quality
Production
PC&L
Purchasing
IT (incl. EDI support)
Engineering
Maintenance
Finance
Human Resources

## Shutdown Prep
[13 empty] | Legend: | Planned
Plant: |  | XXX | [11 empty] | Done
Owner: |  | YYY | [11 empty] | In progress
Date: |  | 2026-05-09 | [11 empty] | Delay
[14 empty] | Wk N | [6 empty] | Wk N+1 | [6 empty] | Wk N+2 | [6 empty] | Wk N+3
Main Actions | Function | [6 empty] | Status |  |  | Date |  |  | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020
| CS | Mfg | PC | Main | ME | SCM | HR | OK | NOK | N/A | Starting | Finishing | Real
Material
No material pending for receiving | S |  | R | [38 empty] | Yes
All boxes must be closed (including plastic bag for cables ties / seals etc..) to avoid contamination | S |  | R | [38 empty] | Yes
Batch Production - pack all splices & kits in production lines (with plastic) | S | R | [39 empty] | Yes
KSK Production - clean all WIP (No kit's / Sub / harnesses) | S | R | [39 empty] | Yes
Guaranty that Non-conforming parts are stored in the RED cage | R |  | S | [38 empty] | Yes
Ensure bundles protection (using cups, no bundle in wait…) |  | R | [39 empty] | Yes
Ensure that no harness is in waiting or out of working process | S | R | [39 empty] | Yes
Move all Finish Goods to the Warehouse (special control for non-standard packages or uncompleted orders) |  | S | R | [38 empty] | Yes
Guaranty that all chemical products are stored in the designated area (PUR components, etc.) |  | R | S | [38 empty] | Yes
Machine
All equipment used on the material movement must be store following the supplier specs |  |  | R | S | [37 empty] | Yes
Move all the extra dies, seals applicator to the die center and keep only the next setup (Manufacturing area) |  | R |  | S | [37 empty] | Yes
Ensure that all dies and seal applicators protected with the correct protection and in the correct storage area |  | S |  | R | [37 empty] | Yes
Collect all the rework tools & tube insertion help tool, from rework operator before holidays |  | R | [39 empty] | Yes
Protect all assembly kit boards, Cable Channels tables with foil |  | S |  | R | [37 empty] | Yes
Execute 1st level maintenance and protect all ROB's |  | R |  | S | [37 empty] | Yes
PUR machines stoppage procedure follow supplier specs and POS |  | R |  | S | S | [36 empty] | Yes
Method
Clean all Manifests, Kitting orders, pre-print labels from lines |  | R | S | [38 empty] | Yes
Keep one harness per line to confirm the ROB conditions (harness already checked); harness must be identified and must be representative (the biggest content) | S | R | [39 empty] | Yes
Management
Did we took into consideration all Customer Requirement (Mails, Letters, Customer Portal notifications)? | R |  | R |  | R | [36 empty] | Yes
Execute / Revise Shutdown / Re Start PFMEA (Risk Analysis) | S | S | S | S | R | S | S | [34 empty] | Yes
Plan shutdown period & restart Facilities activities to guaranty the correct environment conditions (Temperature / Humidity) to preserve components/ finish goods & Equipment integrity (include in Security Checklist Rounds) |  |  |  | R |  |  | S | [34 empty] | Yes
Verify / adjust the Facilities Shutdown and Restart activities (air compress; electricity ; air conditioner; water management etc.) |  |  |  | R | [37 empty] | Yes
Inform suppliers & logistic provider about shut down plan |  |  | R | [38 empty] | Yes
Informing Customer about contingency contact list | R |  | R | [38 empty] | Yes
Release area | Activities Status | [6 empty] | 0%
Legend :
R - Responsible - Those who do the work to achieve the task.
S - Support - Resources allocated to Responsible. Unlike Consulted, who may provide input to the task, Support will assist in completing the task
I - Inform - Those who are kept up-to-date on progress, often only on completion of the task or deliverable; and with whom there is just one-way communication.
Conditionally Released (required action plan)
Release Area
ESCALATION PROCESS
3
2
1
Plant Manager is responsible to Postpone SOP or Require TOP Management (Regional Operations Manager & Regional CS Manager) authorization to start production

## Start-Up Incoming Area
[15 empty] | Legend: | Planned
Plant: | XXX | [14 empty] | Done
Owner: | PCL | [14 empty] | In progress
Date: | 2026-05-09 | [14 empty] | Delay
[16 empty] | Wk N | [6 empty] | Wk N+1 | [6 empty] | Wk N+2 | [6 empty] | Wk N+3
Main Actions | Timing |  |  | Function | [5 empty] | Status |  |  | Date |  |  | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020
| Prior SOP | 1st Day | 1st wk | CS | Mfg | PC | Main | ME | HR | OK | NOK | N/A | Starting | Finishing | Real
Team definition
Team: Quality: XXX ; PC&L: XXX | X | [42 empty] | Yes
Material | [43 empty] | Yes
Verify the exitance of components to be received and communicate any delay / workload concern: 1. Do we have trucks to be unload 2. What are the packaging condition | X |  |  | S |  | R | [37 empty] | Yes
Communicate all urgent components by using the register of urgent components |  | X | X | I | S | R | [37 empty] | Yes
Verify if the components existing in RED cage are according to the Rejection list |  |  | X | R |  | I | [37 empty] | Yes
Man
Map all people from the area / value stream and check their presence on the 1st day to prepare absenteeism / coverage plan - define & prepare the need of back up operator structure for training based on the risk (fatal losses, long illness recovering, quitting the job, etc.) | X | X | X | R |  | R |  |  | S | [34 empty] | Yes
Communicate the absenteeism status and check the operator qualification in receiving and SM (Evaluate people motivation after stoppage using daily / shiftily meetings) |  | X | X | S |  | R |  |  | S | [34 empty] | Yes
Management
Verify IT connection and all Systems are working (SAP, DCIX, etc.) | X |  |  | R |  | R | [37 empty] | Yes
Check list of critical suppliers (If exist; criticity; how long) |  | X |  | I |  | R |  | S | [35 empty] | Yes
Inform suppliers & logistic provider restart plan and check if any abnormal | X |  |  |  |  | R | [37 empty] | Yes
Check with suppliers the open claim and the supplier feedback (Batch certification and sorting stop) |  |  | X | R |  | I | [37 empty] | Yes
Perform LPA in the receiving and SM areas prior to release the area ( EAGP_5-3_MG_14_EN.doc ; Ex.: DOC #1 EAGP_5-3_MG-NAF_14-F02_FR) | X |  |  | S |  | R | [37 empty] | Yes
Release area | X |  |  | Activities Status | [5 empty] | 0%
LPA Result
|  |  |  | Final Score | [5 empty] | 0%
Legend :
R - Responsible - Those who do the work to achieve the task.
S - Support - Resources allocated to Responsible. Unlike Consulted, who may provide input to the task, Support will assist in completing the task
I - Inform - Those who are kept up-to-date on progress, often only on completion of the task or deliverable; and with whom there is just one-way communication.
Conditionally Released (required action plan)
Release Area
ESCALATION PROCESS
3
2
1
Plant Manager is responsible to Postpone SOP or Require TOP Management (Regional Operations Manager & Regional CS Manager) authorization to start production

## Start-Up Cutting & LP Area
[17 empty] | Legend: | Planned
Plant: | XXX | [16 empty] | Done
Owner: | Mfg Cutting | [16 empty] | In progress
Date: | 2026-05-09 | [16 empty] | Delay
[18 empty] | Wk N | [6 empty] | Wk N+1 | [6 empty] | Wk N+2 | [6 empty] | Wk N+3
Main Actions | Timing |  |  | Function | [5 empty] | Deliverable | Criteria | Status |  |  | Date |  |  | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020
| Prior SOP | 1st Day | 1st wk. | CS | Mfg. | PC | Main | ME | HR |  |  | OK | NOK | N/A | Starting | Finishing | Real
Team definition
All shifts Quality: XXX ; Cutting/LP: XXX ; Training: XXX; Engineering : XXX ; Maintenance: XXX ; Reliability : XXX | X | [44 empty] | Yes
Material
Review all wires components status (identification, protection and storage) | X |  |  | S | R | S | [39 empty] | Yes
Check cut leads appearance; if any oxidation | X |  |  | S | R |  |  | S |  | If exist any oxidation all must be identified & rejected | Zero cases | [34 empty] | Yes
Machine
List all preventive maintenance not executed and plan the recovery for all equipment's (due to the outbreak) | X |  |  |  | S |  | R | [38 empty] | Yes
Confirm the equipment preventive maintenance. List all intervention done in order to confirm the validation (EAGP_5-3_MG_05_EN.pptm) | X |  |  | R | S |  | S | [38 empty] | Yes
Check / validate one setup/ machine / shift by the quality auditor (EAEP_5-3_CS_01_EN.pptm Monitoring and Measurement of the Product and Manufacturing Process) assuming all machines are RED classified |  | X | X | R | S | [40 empty] | Yes
List all calibration activities not executed and plan the recovery for all (due to the outbreak) (DOC EAGP_5-3_CS_11_EN Calibration and Control of Inspection, Measurement and Test Equipment) | X |  |  | R | I |  | I | [38 empty] | Yes
Man
No new Operators can be used on this area, however if not possible for New Operators all Set-up must be validated (EAGP_5-3_CS_10_EN.ppt) |  | X | X | R | S | [40 empty] | Yes
Map all people from the area / value stream and check their presence on the 1st day to prepare absenteeism / coverage plan - define & prepare the need of back up operator structure for training based on the risk (fatal losses, long illness recovering, quitting the job, etc.) | X | X | X | S | R | S | S | S | S | If a absenteeism is > than the normal , additional quality gates must be introduced at the backed-up operations. Need to define abs number above which we cannot support and run the area | [35 empty] | Yes
Communicate the absenteeism status and check the operator qualification (evaluate people motivation after stoppage using daily / shiftily meetings) | X | X | X | S | R | S | S |  | S | [36 empty] | Yes
Review the rework operator definition per area / Machine, prepare list to be followed by team leader & Quality Inspector with back up structure preparation planning (ensure list of all rework operators) | X | X | X | S | R |  |  | S | S | If a qualified Rework operator is unavailable, nonconforming product must be quarantined | [35 empty] | Yes
Management | [45 empty] | Yes
Verify IT connection and all Systems are working (CAO, Micrometer connection with machine etc.) | X | X |  | S | R |  | S | S | [37 empty] | Yes
Prepare Quality Communications package based on VOC & VOP | X |  |  | R | S | I | I | S | S | Clear communicate package on local language must include the high hurt issues from VOP/VOC and System compliance | [35 empty] | Yes
Perform the Quality Communication plan at the shift startup by group (5 machines by group) |  | X | X | S | R |  | S | S | S | [36 empty] | Yes
Request and communicate the production planning of the first day to Evaluate the Workload | X |  |  | I | R | S | I | I | I | [36 empty] | Yes
Are Eng. Changes to be applied? | X |  |  | I | I | I | I | R | I | [36 empty] | Yes
Are the Eng. Changes released? | X |  |  | S | S | S | S | R | S | Perfom Process / system release | as per EOS | [34 empty] | Yes
Did we had any Layout change? | X |  |  | S | S | S | S | R | [37 empty] | Yes
Was the layout change released? | X |  |  | S | S | S | S | R |  | Perfom Process / system release | as per EOS | [34 empty] | Yes
Execute surveillance routine in all Cutting Area (Ex.. DOC#2) | X | X | X | R | S |  | S | S | [37 empty] | Yes
Set up a Containment (firewall) with control plan for critical Machines impacted by CC, or as result from Absenteeism (EAGP_4-3_CS_08_EN Containment/Quarantine System for Manufacturing Operations - Customer Protection) | X | X | X | R | S |  | S | S | S | Firewall / Self CS1 KPI | Zero defects / incidences detected at CS1 or pass customer issues audit | [34 empty] | Yes
Perform LPA (EAGP_5-3_MG_14_EN.doc ; Ex,: DOC#1 EAGP_5-3_MG-NAF_14-F02_FR) | X | X |  | S | R | S | S | S | S | [36 empty] | Yes
Release area | X | [9 empty] | Activities Status | 0%
LPA Result
[11 empty] | Final Score | 0%
Legend :
R - Responsible - Those who do the work to achieve the task.
S - Support - Resources allocated to Responsible. Unlike Consulted, who may provide input to the task, Support will assist in completing the task
I - Inform - Those who are kept up-to-date on progress, often only on completion of the task or deliverable; and with whom there is just one-way communication.
Conditionally Released (required action plan)
Release Area
ESCALATION PROCESS
3
2
1
Plant Manager is responsible to Postpone SOP or Require TOP Management (Regional Operations Manager & Regional CS Manager) authorization to start production

## Start-Up FA Area
Plant: | XXX | [15 empty] | Legend: | Planned
Owner: | Mfg | [16 empty] | Done
Line: | ZZZ | [16 empty] | In progress
Date: | 2026-05-09 | [16 empty] | Delay
[18 empty] | Wk N | [6 empty] | Wk N+1 | [6 empty] | Wk N+2 | [6 empty] | Wk N+3
Main Actions | Timing |  |  | Function | [5 empty] | Deliverable | Criteria | Status |  |  | Date |  |  | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020
| Prior SOP | 1st Day | 1st wk. | CS | Mfg. | PC | Main | ME | HR |  |  | OK | NOK | N/A | Starting | Finishing | Real
Team definition - Owner Responsibility
Team 1 (Morning shift): (Quality: ,[From: to: ]); (Production: ,[From: to: ]); (Training: ,[From: to: ]); (ME: ); (PC&L: ,[From: to: ]); (Maintenance: ,[From: to: ]); (Cutting: ) | X | [44 empty] | Yes
Team 2 (Evening Shift) (Quality: ,[From: to: ]); (Production: ,[From: to: ]); (Training: ,[From: to: ]); (ME: ); (PC&L: ,[From: to: ]); (Maintenance: ,[From: to: ]); (Cutting: ) | X | [44 empty] | Yes
Team 3: (Night Shift) (Quality: ,[From: to: ]); (Production: ,[From: to: ]); (Training: ,[From: to: ]); (ME: ); (PC&L: ,[From: to: ]); (Maintenance: ,[From: to: ]); (Cutting: ) | X | [44 empty] | Yes
Define Targets for 1st Week
FTQ, rework rate , Quality Class Product Audit | X | X | X | R | S |  |  | S |  | Need to define based on area evaluation and Requirements | [35 empty] | Yes
Output, absenteeism & downtime | X | X | X | S | R | S | S | S | S | Need to define based on area evaluation and Requirements; Threshold above which we cannot run must be clear identified | [35 empty] | Yes
Material
Check wires / components distribution in the cells according to sign off | X |  |  | S | R | S |  | S | [37 empty] | Yes
Review all wires and components identification ; team leaders to be available to ensure the right identification and good feeding in each line | X |  |  |  | R | [40 empty] | Yes
Check wires expire date in USW station before SOP | X |  |  | R | S |  |  |  |  | if dates are above the define Treshold for US must be segragate and proceed as per POS | > 28 days after cutting date | [34 empty] | Yes
Machine
Make inventory of all projects rework and help tools & fill in the gap's from die center | X |  |  | I | R |  | S | I | [37 empty] | Yes
Order missing rework and help tools that are not available in the Die Center | X |  |  | I | I |  | R | I | [37 empty] | Yes
Ensure that all spare parts are at the required inventory levels as per the MIN / MAX ; audit randomly 10 codes | X |  |  | I | I |  | R | [38 empty] | Yes
Check dummy harnesses conformity for each value stream and do a Surveillance routine on ROB (ALRO) (EAGP_5-3_CS_14_EN Surveillance Routine for ROB/ESB) | X |  |  | S | R |  | S | S | [37 empty] | Yes
Validate ROB station by re-testing a representative harness (the biggest content) keep the label with the Dummy harness label on the Surveillance Routine | X |  |  | R | S |  | S | S | [37 empty] | Yes
Checking the label meet Customer requirement (no information missing, no repeat S/N） | X | X |  | S | S | I | R | I | I | All Specified information must be visible and readible | [35 empty] | Yes
Perform Learning in USW machine, with Process control (EMEA - POS DPEW MEN-MEC 00.05.03.009-2) | X |  |  | S | S |  | R | [38 empty] | Yes
Check the key process conformity and error proofing (DOC #3) * USW machine - DPEW MEN-MEC 00.05.03.009-03 * Heat Shrinking sealing machine parameters vs technical sheet DPEW MEN-MEC 00.11 - 03.009 * All Tie guns DPEW MEN - MEC 00.34_03.009 * All Kits holders * All Board holders * Vision Machine * Torq Machine * Cable Channel * Packaging | X |  |  | R | S |  | S | S |  | Process release label | All processes with green label; for yellow process (conditional release), zero items related to quality | [34 empty] | Yes
List all preventive maintenance not executed and plan the recovery for all equipment's (due to the outbreak) | X |  |  |  | S |  | R | [38 empty] | Yes
Confirm the equipment preventive maintenance effectiveness (EAGP_5-3_MG_05_EN.pptm) | X |  |  | R | S |  | S | [38 empty] | Yes
Method | [45 empty] | Yes
Define list of Critical Process & Workstations | X |  |  | S | S |  |  | R | [37 empty] | Yes
Confirm packaging operator steps conformity in the first harness before SOP |  | X |  | R | S |  |  | S | [37 empty] | Yes
Ensure the Work Instruction use & respect, sign off , SOS , WAM, all needed documents | X |  |  | S | R |  |  | S | [37 empty] | Yes
Apply the specific system respect check list (push-click-pull, help tool usage, self control, …) |  | X | X | S | R |  |  | S | S | Re training plan for push-click pull | Training module available / Schedule / Status report out | [34 empty] | Yes
Man
Map all people from the area / value stream and check their presence on the 1st day to prepare absenteeism / coverage plan - define & prepare the need of back up operator structure for training based on the risk (fatal losses, long illness recovering, quitting the job, etc.) | X | X | X | S | R | S | S | S | S | If a absenteeism is > than the normal , additional quality gates must be introduced at the backed-up operations. Need to define abs number above which we cannot support and run the area | [35 empty] | Yes
Communicate the absenteeism status and check the operator qualification (evaluate people motivation after stoppage using daily / shiftily meetings) | X | X |  | S | R |  |  |  | S | [36 empty] | Yes
Review the rework operator definition per Value Stream, prepare list to be followed by team leader & Quality Auditor with back up structure preparation planning (ensure list of all rework operators) | X | X | X | S | R |  |  | S | S | If a qualified Rework operator is unavailable, nonconforming product must be segregated | [35 empty] | Yes
Define Support Structure (SOP Team) based on absenteeism, Quality performance prior to shutdown and Capacity Study | X | X | X | S | R | S | S | S | S | [36 empty] | Yes
Define inspection level by family based on pre-shutdown quality performance, absenteeism and capacity ramp-up | X | X | X | R | S | I | I | I | I | If there has been an escape in the past 60 days (Feb + Mar), increased inspections are required | [35 empty] | Yes
Re Certify Containment Operators on the Control Plan & validate them (EAGP_4-3_CS_08_EN Containment/Quarantine System for Manufacturing Operations - Customer Protection) | X: X; R: S; S: S; I: R | [36 empty] | Yes
Management
Verify IT connection and all Systems are working (WMS, PB2O, OPS, ALS) | X | X |  | S | R | S | S | S | [37 empty] | Yes
Prepare experience-based back-up structure for critical station (review the versatility matrix according to the new update of critical workstation) | X | X | X | S | R |  | S | S | S | If regular operators are not present for duty on a critical operation, an additional quality gate must be introduced, even if the backup is qualified (might have been a while since last on the job) | [35 empty] | Yes
Schedule low PN's content for SOP and minimize set-up for 3 first days (1 PN per shift) | X: X; R: I; S: S; I: R; I: S | [36 empty] | Yes
Ensure that all production planning are available (no missing kitting orders or manifests; no mistakes) | X: X; R: I; S: S; I: R; I: I | [36 empty] | Yes
Define Rump up Curve for the first week of production and reflect in Capacity study | X: X; R: S; S: S; I: R; I: S | Production scheduling ramp up / criteria to move from one stage to other. | Available / approved | [34 empty] | Yes
Awareness campaign for material respect (5S) |  | X | X | S | R | S | S | S | S | [36 empty] | Yes
Perform Special Quality refreshment (local language) covering Customer feedbacks, external sorting items, internal issues and forbidden operations per shift (Communication per value stream) / last 60 days customer concerns |  | X | X | S | S |  |  | S | R | 100% team members pass through awareness campaign / campaign deck. | Attendance list available | [34 empty] | Yes
Are Eng. Changes to be applied? | X |  |  | S | S | S | S | R | S | [36 empty] | Yes
Are the Eng. Changes released? | X |  |  | S | S | S | S | R | S | Perfom Process / system release | as per EOS | [34 empty] | Yes
Did we had any Layout change? | X |  |  | R | S | S | S | S | [37 empty] | Yes
Was the layout change released? | X |  |  | R | S | S | S | S |  | Perfom Process / system release | as per EOS | [34 empty] | Yes
Self CS1 results / Last 60 days Customer Complaint Action effectiveness (monitoring audit) | X: X; X: X; R: R; S: S; I: S | Firewall / Self CS1 KPI | Zero defects / incidences detected at CS1 or pass customer issues audit | [34 empty] | Yes
Product audit to be performed per shift / day by the quality auditor for 5 piece every lot and 1 KSK harness (EAEP_5-3_CS_01_EN.pptm Monitoring and Measurement of the Product and Manufacturing Process) assuming all lines are RED classified | X: X; X: X; R: R; S: S | Add a First Piece product audit | [35 empty] | Yes
Define & execute in line quality gates, based on new team members / past defects / critical processes | X | X | X | R | S |  |  | S |  | Value stream lay out with QG, list of inspection items by QG. | QG staffed/trained/in place | [34 empty] | Yes
Execute Labeling Audit (EAGW_0-1_CS_00-01-F10_EN OSA Flow 5 - DCS, DEC, DEEDS - Labeling) | X: X; R: R; S: S; I: S | [36 empty] | Yes
Set-up a Containment (firewall) with control plan based on VOC / VOP or as result from Absenteeism | X | X | X | R | S |  | S | S | S | Robust containment process for product before shipping. | Containment stations staffed/hardware set up/trained | [34 empty] | Yes
Perform System Release (EAGP_4-3_CS-EUO_05-F01_EN Process Release Checklist) |  | X |  | S | S | S | S | R | S | [36 empty] | Yes
Confirm that all define Controls are in place |  | X | X | R | S | S | S | S | S | [36 empty] | Yes
Perform LPA (EAGP_5-3_MG_14_EN.doc ; Ex,: DOC#1 EAGP_5-3_MG-NAF_14-F02_FR) |  | X |  | S | R | S | S | S | S | [36 empty] | Yes
Release area | [10 empty] | Activities Status | 0% | bar: X
System Release
LPA Result
[11 empty] | Final Score | 0%
Legend :
R - Responsible - Those who do the work to achieve the task.
S - Support - Resources allocated to Responsible. Unlike Consulted, who may provide input to the task, Support will assist in completing the task
I - Inform - Those who are kept up-to-date on progress, often only on completion of the task or deliverable; and with whom there is just one-way communication.
Conditionally Released (required action plan)
Release Area
ESCALATION PROCESS
3
2
1
Plant Manager is responsible to Postpone SOP or Require TOP Management (Regional Operations Manager & Regional CS Manager) authorization to start production

## Template
[15 empty] | Legend: | Planned
Plant: | XXX | [14 empty] | Done
Owner: | YYY | [14 empty] | In progress
Date: | 2026-05-09 | [14 empty] | Delay
[16 empty] | Wk N | [6 empty] | Wk N+1 | [6 empty] | Wk N+2 | [6 empty] | Wk N+3
Main Actions | Timing |  |  | Function | [5 empty] | Status |  |  | Date |  |  | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020 | __ / __ / 2020
| Prior SOP | 1st Day | 1st wk | CS | Mfg | PC | Main | ME | HR | OK | NOK | N/A | Starting | Finishing | Real
Team definition
Material
Machine
Method
Man
Management
Release area | X |  |  | Activities Status | [5 empty] | 0%
Q Audit Result
LPA Result
|  |  |  | Final Score | [5 empty] | 0%
Released YES NO
Legend :
R - Responsible - Those who do the work to achieve the task.
S - Support - Resources allocated to Responsible. Unlike Consulted, who may provide input to the task, Support will assist in completing the task
I - Inform - Those who are kept up-to-date on progress, often only on completion of the task or deliverable; and with whom there is just one-way communication.
Conditionally Released (required action plan)
Release Area
ESCALATION PROCESS
3
2
1
Plant Manager is responsible to Postpone SOP or Require TOP Management (Regional Operations Manager & Regional CS Manager) authorization to start production

## Reference
LPA checklist for all areas

## Reference DOC #2 EN
Cutting process audit
LP process audit

## Reference DOC #3 EN
Final Assembly process audit
Final Assembly Monitoring audit

## Process KPIs
|  |  | Document reference measures form before production shutdown |  | Restart monitoring
|  |  | Wk N |  |  | Wk N+1 |  |  | Wk N+2 |  |  | Wk N+3 |  |  | Wk N+4 |  |  | Wk N+5 |  |  | Wk N+6 |  |  | Wk N+7 |  |  | Wk N+8 |  |  | Wk N+9 |  |  | Wk N+10
Metric | KPI | Target | Actual | Status | Actual | Status | Progress | Actual | Status | Progress | Actual | Status | Progress | Actual | Status | Progress | Actual | Status | Progress | Actual | Status | Progress | Actual | Status | Progress | Actual | Status | Progress | Actual | Status | Progress | Actual | Status | Progress
Product Audit | QC |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| % OS Yield |  |  | 0% |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0
Pass Rate | Pass Rate |  |  | 0% |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0
Line FTQ | PPM |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
Absenteeism | % of Absenteeism |  |  | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0

## Revision index
Rev | Date | Action / Purpose | Author
001 | 2020-06-30 | File creation ; Update related to COVID-19; Update from with AP inputs; Considering PSA-OV start-up procedure; Adjustment according to David Hines suggestion; Include the Release Criteria and change "Activities Status" formula to exclude the N/A from the result; Added "Process KPIs" tab and adjustment to the format of EOS documentation form | Antonio Andrade
2 | Oct.2023 | Global form renumbered linked with Corporate procedure ; old GL form obsoleted . | Charlotte Widen
3 | Dec.2025 | Changed the template and format, renumbered according with EDS. New Doc Owner Anca Crasta . | Alina Dragoi